## Start Here
CMMC Level 2 Readiness Toolkit for Small Government Contractors
Purpose | Use these worksheets with the Mirzayan LLC workbook to scope CUI/FCI, organize evidence, track gaps, and prepare a practical 30/60/90-day action plan.
Important disclaimer | Educational readiness aid only. Not legal advice, not a certification guarantee, and not a substitute for your contracting officer, assessor/C3PAO, attorney, MSP, or cybersecurity advisor.
Recommended workflow
1 | Confirm whether you handle CUI/FCI and document where it flows.
2 | Inventory systems, users, vendors, MSP access, cloud services, and evidence.
3 | Score readiness by area and identify top gaps.
4 | Build the evidence binder and assign owners/dates.
5 | Turn top gaps into a 30/60/90-day remediation roadmap.
6 | Use the consultation prep worksheet before speaking with Mirzayan or another advisor.
Tabs included
Gap Register | Editable worksheet
Evidence Binder | Editable worksheet
Vendor MSP Matrix | Editable worksheet
Readiness Scorecard | Editable worksheet
30-60-90 Roadmap | Editable worksheet
CUI Flow Map | Editable worksheet
Mirzayan LLC CTA | Need help turning these worksheets into an implementation plan? Request a readiness consultation with Mirzayan LLC.

## Dashboard
Readiness Dashboard
Area | Score | Interpretation | Next Action
CUI/FCI scope clarity |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Systems inventory |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
User/access inventory |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Evidence binder |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
MFA/access controls |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Logging/monitoring |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Incident response |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Risk/gap tracking |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Vendor/MSP clarity |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.
Internal ownership |  | 0 not started / 1 partial / 2 documented needs work / 3 evidence-ready | If below 2, add a gap-register item with owner/date.

## Gap Register
Gap ID | Control Family | Gap Description | Business/Contract Impact | Risk Rating | Recommended Action | Owner | Target Date | Status | Evidence Needed | Notes | How to use this sheet
G-001 | Access Control | MFA not verified across all scoped systems | May weaken readiness evidence | High | Inventory systems and enable/verify MFA |  |  | Open | MFA configuration screenshots, user list |  | Capture every readiness gap, assign an owner/date, and use status updates during weekly remediation reviews.
G-002 | System and Information Integrity | Patch evidence not retained | Hard to prove remediation discipline | Medium | Create patch review log |  |  | Open | Patch dashboard export, tickets
G-003 | Assessment and Monitoring | System boundary not documented | Scope uncertainty drives cost/risk | High | Draft scoped system description |  |  | Open | SSP/system diagram

## Evidence Binder
Evidence ID | Control Family | Evidence Category | Evidence Name | System/Scope | Owner | Location/Link | Review Frequency | Current? | Reviewer Notes | How to use this sheet
E-001 | Access Control | Access Review | Current user/access export | Email, file storage, endpoint management |  |  | Quarterly | No |  | List where evidence lives before anyone asks for it. Screenshots, policies, tickets, exports, meeting notes, and diagrams all count as evidence candidates.
E-002 | Identification and Authentication | MFA | MFA settings screenshot/export | Identity provider/cloud apps |  |  | Quarterly | No
E-003 | Incident Response | Plan | Incident response plan and contact list | Company-wide |  |  | Annual | No
E-004 | Risk Assessment | Vulnerability Management | Scan report and remediation tracker | Endpoints/cloud/network |  |  | Monthly | No

## Vendor MSP Matrix
Vendor/MSP/Subcontractor | Function | Touches CUI? | Admin Access? | Systems Accessed | Security Responsibility | Evidence Expected | Contract Terms Reviewed? | Review Date | Owner | Notes | How to use this sheet
MSP | IT support and remote administration | Unsure | Yes | Endpoints, identity, email | Patch support, account support, backup support | Ticket records, access list, remote support logs | No |  |  |  | Clarify what your MSP, cloud providers, subcontractors, and vendors actually own. Do not assume responsibility without writing it down.
Cloud email/file provider | Email and file storage | Unsure | Yes | Email, file storage | Platform security controls, logs/configuration exports | MFA settings, audit logs, retention settings | No
Subcontractor | Project support | Unsure | No/Unknown | Project data as assigned | Protect flowed-down information | Acknowledgment/flow-down evidence | No

## Readiness Scorecard
Area | Score 0-3 | Meaning | Evidence/Notes | Owner | Next Action | How to use this sheet
CUI/FCI scope clarity |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready |  |  |  | Score each area 0–3. Anything below 2 should usually produce a gap-register item.
Systems inventory |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
User/access inventory |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Evidence binder |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
MFA/access controls |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Logging/monitoring |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Incident response |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Risk/gap tracking |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Vendor/MSP clarity |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready
Internal ownership |  | 0 not started; 1 partial; 2 documented needs work; 3 evidence-ready

## 30-60-90 Roadmap
Phase | Action | Why It Matters | Owner | Target Date | Status | Evidence/Output | Notes | How to use this sheet
Days 1-30 | Confirm CUI/FCI scope | Scope drives every readiness decision |  |  | Open | Contract review notes, CUI flow map |  | Turn the gap register into an action plan. Prioritize scope, MFA/access, evidence, vendor responsibilities, logging, IR, and high-risk technical gaps.
Days 1-30 | Complete systems and user inventory | Find systems/users that may be in scope |  |  | Open | Systems inventory, user list
Days 1-30 | Enable/verify MFA on key systems | Common high-impact quick win |  |  | Open | MFA screenshots/export
Days 31-60 | Review vendor/MSP responsibilities | Avoid responsibility gaps |  |  | Open | Responsibility matrix
Days 31-60 | Build evidence binder | Prepare for review and reduce scramble |  |  | Open | Evidence binder index
Days 61-90 | Perform internal readiness review | Validate readiness before external pressure |  |  | Open | Scorecard, gap register update
Days 61-90 | Prioritize remediation budget | Tie technical fixes to business risk |  |  | Open | Priority matrix

## CUI Flow Map
Flow Step | Source/Sender | System/Location | Data Type | CUI? | Recipient/Destination | Protection Used | Owner | Evidence Available | Gap/Notes | How to use this sheet
Receive |  |  |  | Unsure | [5 empty] | Document receive, store, process, transmit, and archive/delete paths. This is the core scope conversation.
Store |  |  |  | Unsure
Process |  |  |  | Unsure
Transmit |  |  |  | Unsure
Archive/Delete |  |  |  | Unsure